## Tech Stack
⚡ QuickOff — Tech Stack
Technologies, tools, and dependencies used in QuickOff v1.3
# | Layer | Technology | Version / Detail | Purpose | Dependency Type | Notes
1 | UI Runtime | mshta.exe (HTA Host) | Shipped with Windows XP+ | Hosts and renders the HTA widget | OS Built-in | IE Trident rendering engine; no admin needed
2 | Rendering | IE/Trident Engine | IE 11 compatible | HTML + CSS + JS rendering inside mshta.exe | OS Built-in | No CSS Grid; no modern fetch API; no emoji font
3 | UI Language | HTML 4 / CSS 2 / ES5 JS | IE-compatible subset | Widget layout, styles, and all interaction logic | None | Avoids modern APIs unsupported by Trident
4 | Shell Exec | WScript.Shell (ActiveX) | Windows built-in COM | Run shutdown, rundll32, PowerShell commands | OS Built-in | Pure JS — no VBScript bridge (breaks Win11)
5 | File I/O | Scripting.FileSystemObject | Windows built-in COM | Write temp PS1 file for shortcut creation | OS Built-in | Also used for icon path resolution
6 | HTTP / API | Msxml2.XMLHTTP.6.0 | Windows built-in COM | Async GitHub Releases API call for update check | OS Built-in | eval() used to parse JSON (IE compat)
7 | Icon Format | ICO (multi-size) | 16/32/48/64/256 px | App icon for widget, shortcut, File Explorer | External | Generated with Python + Pillow during dev
8 | Icon Delivery | Base64 data URI | Embedded in .hta | Display logo inside app; no external file needed | None | Both 48 px (About) and 14 px (footer) copies
9 | Registry | WScript.Shell RegRead/Write | HKCU only | Autostart, icon class, first-run flag | OS Built-in | No admin — all under HKCU
10 | Shortcut | PowerShell WScript.Shell | Temp .ps1 file approach | Create Desktop .lnk with icon on first launch | OS Built-in | More reliable than direct COM in HTA context
11 | CLI Launcher | launch.bat | Batch script | Trigger any power action from terminal / scheduler | None | Embeds icon as base64; extracts before launch
12 | Setup Util | setup.bat | Batch script | Autostart, icon registration, shortcut creation | None | Uses PowerShell for shortcut; reg for icon
13 | Packaging | ZIP archive | No installer | Distribution format | None | Extract and double-click — no setup.exe
14 | Version Ctrl | Git + GitHub | github.com/yashwanth.../QuickOff | Source control and releases | External | Releases tagged as v1.x
15 | Update Check | GitHub Releases API v3 | api.github.com | Latest release tag comparison at launch | External / free | User-Agent header set to QuickOff/1.3
16 | Icon Gen (dev) | Python + Pillow | PIL/Pillow | Generate .ico file during development | Dev only | Not shipped in release ZIP

## Feature Tracker
⚡ QuickOff — Feature Tracker
All planned and shipped features with status and version
# | Feature | Category | Status | Version | Priority | Description | Notes
1 | 6 Power Actions | Core | ✅ Shipped | v1.0 | P0 | Hibernate, Sleep, Shut Down, Restart, Lock, Sign Out | All via WScript.Shell commands
2 | Confirm Overlay | UX | ✅ Shipped | v1.0 | P0 | Confirm prompt before executing any power action | Prevents accidental triggers
3 | Delay Timer | Core | ✅ Shipped | v1.0 | P1 | Schedule any action by N seconds with countdown | Live tick in status bar
4 | Draggable Window | UX | ✅ Shipped | v1.0 | P2 | Drag widget anywhere on screen via footer label | Re-added in v1.1.1 after regression
5 | CLI Launcher | Developer | ✅ Shipped | v1.0 | P1 | launch.bat supports all 6 actions + delay + abort | Supports Task Scheduler integration
6 | Autostart via setup.bat | Developer | ✅ Shipped | v1.0 | P2 | HKCU Run registry key, no admin required | Enable/disable in setup.bat
7 | Light / Dark Theme | UX | ✅ Shipped | v1.2 | P1 | Toggle with ☾/☀ button; all elements re-coloured | Light is default since v1.4.0
8 | Custom App Icon (.ico) | Branding | ✅ Shipped | v1.4.1 | P1 | Amber lightning bolt, 5 sizes, referenced via ICON= | Win11 ignores ICON= for title bar — known limit
9 | Logo Embedded in HTA | Branding | ✅ Shipped | v1.5.1 | P2 | Base64 data URI logo in About overlay and footer | No external .ico needed at runtime
10 | About Panel | UX | ✅ Shipped | v1.3.1 | P2 | Version, MIT license, author, GitHub link overlay | ℹ button in footer
11 | Auto-Update Check | Feature | ✅ Shipped | v1.3.0 | P1 | GitHub Releases API check on launch; update badge | Async — UI never blocks
12 | File Explorer Icon | UX | ✅ Shipped | v1.5.5 | P2 | setup.bat registers htafile DefaultIcon in HKCU | Requires running setup.bat once
13 | Auto Desktop Shortcut | UX | ✅ Shipped | v1.3 | P1 | First-launch PowerShell shortcut creation | Registry flag prevents repeat creation
14 | Remove Startup Manager Tab | UX | ✅ Shipped | v1.4.0 | P1 | Simplified to single power panel, no tab bar | Removed in v1.4.0
15 | Compact Window Size | UX | ✅ Shipped | v1.5.2 | P3 | 250×330 px optimised for all 6 actions visible | Bottom-right auto-position
16 | Tray Icon Support | Feature | 📋 Planned | v1.4 | P1 | System tray presence via PowerShell NotifyIcon | Requires external helper
17 | Global Hotkey Trigger | Feature | 📋 Planned | v1.5 | P1 | Win+Q or custom hotkey to show/hide widget | AutoHotkey or AHK-less approach
18 | WinForms / WPF Migration | Platform | 📋 Planned | v2.0 | P1 | Replace HTA for full Win11 icon + transparency support | Breaks the 'zero install' constraint — TBD
19 | Custom Action Slots | Feature | 🔁 Backlog | - | P3 | User-defined slots: launch app, run script, open URL
20 | Per-Action Confirm Toggle | UX | 🔁 Backlog | - | P3 | Allow some actions to skip confirm overlay
21 | Compact Icon-Only Mode | UX | 🔁 Backlog | - | P3 | Very small widget showing only icons, no labels

## Issue Tracker
⚡ QuickOff — Issue Tracker
Known bugs, regressions, and limitations with resolution status
ID | Title | Category | Severity | Status | Version Found | Version Fixed | Description | Fix / Workaround
BUG-001 | doAction clears pending before check | Logic | 🔴 Critical | ✅ Fixed | v1.1.0 | v1.1.1 | hideOv() cleared 'pending' before action check — every button silently did nothing after confirm | Capture pending into local var before hideOv()
BUG-002 | Lock PC not working | Shell | 🟠 High | ✅ Fixed | v1.1.0 | v1.1.1 | LockWorkStation ran without cmd /c wrapper — failed silently in WScript.Shell context | Wrapped in cmd /c
BUG-003 | Sleep not reliable | Shell | 🟠 High | ✅ Fixed | v1.1.0 | v1.1.1 | SetSuspendState ran without cmd /c — unreliable via WScript.Shell | Wrapped in cmd /c
BUG-004 | Window not draggable | UX | 🟡 Medium | ✅ Fixed | v1.1.0 | v1.1.1 | Drag handler lost when title bar removed in v1.1.0 | Re-added drag handler to footer label
BUG-005 | VBScript bridge breaks on Win11 | Platform | 🔴 Critical | ✅ Fixed | v1.1.x | v1.2.0 | JS-to-VBScript bridge throws script error on every button press in Windows 11 | Replaced entirely with pure JS ActiveXObject
BUG-006 | Dark theme text invisible | UI | 🟠 High | ✅ Fixed | v1.4.x | v1.5.0 | Dark mode colours too close to background — text unreadable | Bumped all dark text to #ccc / #888 / #60a5fa
BUG-007 | GitHub link wrong repo | Feature | 🟠 High | ✅ Fixed | v1.5.x | v1.3 | GITHUB_REPO pointed to PurgeKit instead of QuickOff | Corrected to yashwanthramsomireddy/QuickOff
BUG-008 | Desktop shortcut path with spaces fails | Feature | 🟠 High | ✅ Fixed | v2.3 | v1.3 | window.location.pathname left %20 encoded — FSO couldn't resolve path | Switched to href + unescape()
BUG-009 | Shortcut COM creation silent failure | Feature | 🟠 High | ✅ Fixed | v2.3 | v1.3 | WScript.Shell.CreateShortcut in HTA context silently failed | Replaced with PowerShell temp PS1 file approach
LIM-001 | Title bar icon ignored on Win11 | Platform | ℹ️ Info | ⚠️ Known Limit | v1.0 | - | Windows 11 ignores ICON= in HTA:APPLICATION; mshta.exe icon always shows | No workaround — OS-level restriction
LIM-002 | IE rendering engine | Platform | ℹ️ Info | ⚠️ Known Limit | v1.0 | - | No CSS Grid, no fetch, no modern JS in HTA — limited to IE-compatible code | Design around IE constraints; migrate to WinForms in v2.0
LIM-003 | SINGLEINSTANCE not always enforced | Feature | 🟢 Low | ⚠️ Known Limit | v1.0 | - | SINGLEINSTANCE=yes only works when mshta.exe is on PATH and same file path is used | Expected behaviour; document in README
LIM-004 | Explorer icon requires setup.bat run | UX | 🟢 Low | ⚠️ Known Limit | v1.5.5 | - | File Explorer shows default HTA icon until setup.bat is run once | Step documented in README

## GitHub
⚡ QuickOff — GitHub Info & Release Log
Repository details, release history, and download tracking
Repository Info
Repository | https://github.com/yashwanthramsomireddy/QuickOff
Owner | Yashwanth Ram Somireddy (TeamExyKings)
Releases Page | https://github.com/yashwanthramsomireddy/QuickOff/releases
Issues | https://github.com/yashwanthramsomireddy/QuickOff/issues
License | MIT
Primary Branch | main
Stars | — update manually
Forks | — update manually
Watchers | — update manually
Release Log
Tag | Date | Title | Key Changes | ZIP Name | Downloads | Notes
v1.3 | 2026-08-27 | Auto Desktop Shortcut | Auto shortcut on first launch; correct GitHub repo; path resolution fix | QuickOff-v1.3.zip | — | Current release
v1.2 | 2026-08-26 | VBScript Removal | Removed VBScript bridge (broke Win11); light/dark toggle added | QuickOff-v1.2.zip | —
v1.1 | 2026-08-26 | UI Redesign | Compact single-column list; fixed doAction pending bug; draggable window | QuickOff-v1.1.zip | —
v1.0 | 2026-08-26 | Initial Release | Widget, 6 actions, delay timer, confirm overlay, autostart, CLI | QuickOff-v1.0.zip | — | First public release

## Donation
⚡ QuickOff — Donation & Support
Support tiers, links, and contributor log
Donation Platforms
Platform | Link | Handle | Status | Notes
GitHub Sponsors | https://github.com/sponsors/yashwanthramsomireddy | yashwanthramsomireddy | — Add link | Preferred for developers
Buy Me a Coffee | https://www.buymeacoffee.com/ | — Add handle | — Add link | One-time or monthly
Ko-fi | https://ko-fi.com/ | — Add handle | — Add link | One-time or monthly
PayPal | https://paypal.me/ | — Add handle | — Add link | One-time
Patreon | https://www.patreon.com/ | — Add handle | — Add link | Monthly tiers